## Sheet1
|  |  |  | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Responsible | Activity | Activity Details |  | 2016-03-03 | 2016-03-10 | 2016-03-17 | 2016-03-24 | 2016-03-31 | 2016-04-07 | 2016-04-14 | 2016-04-21 | 2016-04-28 | 2016-05-05 | 2016-05-12 | 2016-05-19 | 2016-05-26
|  |  |  | 0 | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 84
DD | Process Mapping | Resource Requirements | Planning |  | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 70 | 77 | 84 | 546
|  |  | Progress | [13 empty] | 8.333%
DD | Loss & Waste Analysis | Identified and Qualified | Planning |  | 7 | 14 |  | 7 | 14 | 21 | 28 | 35 | 42 | 49 | 56 | 63 | 336
Progress
GP/DD | Loss & Waste Analysis | Profit improvement projects | Planning |  |  |  | 21 | 8.333% 336: #DIV/0!
Progress
GP | Loss & Waste Analysis | Initial actions to be agreed | Planning |  |  |  |  | 8.333% 336: 0
|  |  | Progress |  |  |  |  | 8.333% 336: #DIV/0!
BP/NK | Daily Operational Review | Introduce problem solving | Planning | bar: 7
|  |  | Progress |  |  |  | X
| Daily Operational Review | Maintenance to participate | Planning | bar: 7 to 42
Progress
GP | Daily Operational Review | BM/IM separate meetings | Planning | bar: 7 to 42
Progress
BP/NK | Daily Operational Review | Standard Agenda | Planning | bar: 7 to 14
Progress
BP/NK | Daily Operational Review | Formal GAP list | Planning | bar: 7 to 14
|  |  | Progress |  |  |  | X
GP/DD | Develop Problem solving | PS Training | Planning |  |  |  |  | 8.333% 336: 0
| (PS) Skills |  | Progress |  |  |  |  | 8.333% 336: #DIV/0!
GP |  | Venues, Communication,Catering | Planning | bar: 7 to 21
Progress
GP/DD | TF Meetings |  | Planning | bar: 7 to 21
Progress
BP | Triggers for MDT Problem Solving | Developed | Planning | bar: 7 to 21
Progress
| Triggers for MDT Problem Solving | To be Introduced | Planning | bar: 28 to 49
Progress
NK | Launch + Track PIP's Projects | Setting in IM | Planning | bar: 7 to 14
Progress
BP | Launch + Track PIP's Projects | BM PVC change over reduction | Planning | bar: 7 to 14
Progress
BP/CB | Launch + Track PIP's Projects | Reducing non-recoverable scrap | Planning | bar: 7 to 14
|  | in BM PE. | Progress
|  | Other improvement initiatives | Planning | bar: 7 to 14
Progress
JB | Launch + Track PIP's Projects | Reducing the energy bill | Planning | bar: 7 to 14
JB |  |  | Progress
| Launch + Track PIP's Projects | Redundant Engineering spares | Planning | bar: 7 to 14
Progress
GP/DD | Train Work Teams in basic |  | Planning
| Problem Solving |  | Progress